## Sheet1
Steps | Modules | Sub-Tasks | Planning Phase | Implementation Phase
Note: Use the sections which you feel are valid for your project.
Business & Data Understanding
| Define the Scope of the ML Application | Business Problem | Scalable Global Salary Intelligence System | Predict global salaries for HR/tech jobs based on job title, experience, company size, and other features.
|  | Business Objectives (maximum 4 to 5 words & to the extent possible please use terms such as Minimize & Maximize) | Maximize salary prediction accuracy for global roles | Minimize salary prediction error; maximize accuracy and user trust.
Success Criteria
|  | Business Success Criteria | Minimize data inconsistency <= 5%, | Accurate salary predictions lead to better hiring decisions and improved HR planning.
|  | ML Success Criteria | Maximize prediction accuracy >= 90%, Achieve >90% R² on validation data | RMSE < threshold (e.g., $5000); R² > 0.85 on test data; model generalizes well to new data.
|  | Economic Success Criteria | 15% increase in customer accucation, Reduce compensation benchmarking costs by 30% | Cost-effective deployment (runs on local hardware); improves HR efficiency and reduces manual estimation errors.
Feasibility
|  | Applicability of ML technology | ML models - Linear Regression, Random Forest Regressor, XGBoost Regressor. Technology and tools - Scikit-learn,XGBoost,MLflow,SHAP,Pandas,NumPy,Apache Airflow,Flask,FastAPI,Evidently AI,Matplotlib,Seaborn | Regression and ensemble models are suitable for numeric salary prediction; sufficient data available.
|  | Legal constraints | Fairness and Anti-Discrimination,Masking Salary Data | Data is anonymized; no personal identifiers; complies with company and local data privacy laws.
|  | Requirements on the application | Scalable Architecture, Robust to Missing/Noisy Data, Automated Data & Model Drift Detection | Must be accessible via web (Streamlit); predictions in < 1s; easy user interface; robust to missing or unusual input.
Data Collection
|  | Data version control | Track and version all data changes | Data snapshots stored in PostgreSQL; versioned CSV exports for reproducibility.
Data Quality Verification
|  | Data description | Multinational salary dataset with job, experience, compensation, and currency features; target is adjusted_total_usd. | Features: job_title, experience_level, employment_type, company_size, company_location, base_salary, adjusted_total_usd, salary_in_usd, etc.
|  | Data requirements | Tabular, real-world salary data with standardized job, experience, company, and compensation fields; target: adjusted_total_usd. | Sufficient records for all job types and locations; minimal missing values; representative of global workforce.
|  | Data verification | Verify data for completeness, correctness, consistency, and proper formatting before use. | Outlier detection (IQR), missing value analysis, value range checks, categorical value validation.
Data Preparation
Select Data
|  | Feature selection | currency,salary_currency,total_salary maybe dropped as they include IDs, random currencies whioch might be not useful | Selected based on domain knowledge and feature importance: job_title, experience_level, company_size, company_location, base_salary, etc
|  | Data selection | Select records with complete job, experience, company, and compensation fields; exclude rows with critical missing or invalid values. | Exclude rows with missing critical features; filter outliers; balance job types if possible.
|  | Unbalanced Classes | Unbalanced classes may be present in experience_level, employment_type, company_size, and company_location columns. | Not applicable (regression problem), but check for distribution skew
Clean Data
|  | Noise reduction |  | Remove or correct inconsistent entries (e.g., erroneous salaries)
|  | Data imputation | Fill missing values using mean, median, mode, regression, or MICE techniques.(experience_level ) | Impute missing values with median/mode or model-based imputation
Construct Data
|  | Feature engineering | Standardize job_title, one-hot encode categorical columns, impute missing values, and normalize salaries using currency conversion. | Log-transform base_salary; frequency encoding for company_location; target encoding for job_title.
|  | Data augmentation | Will try to introduce realistic inconsistencies in experience_level and salary_currency to enhance model generalization and robustness. | Not applicable (tabular regression).
Standardize Data
|  | File format | CSV file format | Pandas DataFrames; CSV for exports; PostgreSQL for storage.
|  | Normalization | Normalize salary-related columns (base_salary, bonus, stock_options, total_salary, adjusted_total_usd) using Min-Max scaling or Z-score standardization. | StandardScaler for numeric features in the pipeline.
Modeling
Literature research on similar problems
| Define quality measures of the model | Accuracy | grater then 90% | RMSE, R² on test and validation sets.
|  | Performance | Evaluate speed and efficiency of model predictions and training. | Inference time < 1s; batch scoring supported.
|  | Robustness | Assess model stability under data variations and noise.(<5% drop in accuracy with 10% noise) | Handles missing/unusual input gracefully; robust to outliers.
|  | Scalability | Ensure model maintains performance with increasing data size. | Modular code; can retrain on larger datasets.
|  | Explainability | Ability to interpret model decisions (e.g., SHAP, LIME).(Top 5 features explain >80% variance) | Feature importance via SHAP/sklearn; clear user feedback.
|  | Model Complexity | Balance between simplicity and predictive power.(<50 features, model depth <10) | Prefer simpler models if similar performance; avoid overfitting
|  | Resource Demand | Computational and memory requirements for training and inference.(<8 GB RAM, <2 CPU core usage) | Runs on standard workstation; no GPU required for inference.
| Model Selection |  | XGBoost, Random Forest Regressor , Linear Regression | based on best r^2 , here it I random forest
| Incorporate domain knowledge |  | HR insights (like job levels and location-based pay) to improve data cleaning, feature creation, and model accuracy | HR domain knowledge used for feature selection and outlier handling.
| Model training |  | Fit selected models (like XGBoostregressor or Random Forest Regressor or Linear Regressor) on the prepared dataset to learn how features relate to total salary.
Using unlabeled data and pre-trained models
| Model Compression |  | Reduce model size for efficient deployment(< 50 MB, < 100 ms per prediction)
| Ensemble methods |  | Improve prediction accuracy with model ensembles(≥ 5% gain in R² compared to single model) | Random Forest, Gradient Boosting, XGBoost for improved accuracy.
| Assure reproducibility |  | Ensure consistent training and results replication.(MLflow version tracking, seed control) | Code versioned (Git); data snapshots saved; random seeds set.
|  | Method reproducibility |  | Preprocessor and model saved as .pkl; same pipeline for training and inference.
Result reproducibility
|  | Experimental Documentation |  | MLflow for experiment tracking; all metrics and parameters logged.
Evaluation
| Validate performance |  | RMSE, MAE, R² Score, Cross-validation,(R² > 0.85, RMSE < $5000)
| Determine robustness |  | Robustness Index, Stress Tests, Sensitivity Analysis(< 10% variance in outputs under perturbation) | Test on holdout data; test with edge-case user inputs in Streamlit app.
| Increase explainability for ML practitioner & end user |  | SHAP, Feature Importance, LIME | Feature importance visualized; user-friendly explanations in app.
| Compare results with defined success criteria |  | Salary Error Margin, Coverage Rate (≤ 10% error in adjusted_total_usd predictions) | RMSE and R² compared to targets; business review of predictions.
Deployment
| Define inference hardware |  | Select optimal hardware for latency, cost, and scalability | Local server or cloud VM; no special hardware needed.
| Model evaluation under production condition |  | Latency, Throughput, Accuracy under load () | flask app tested in production-like environment; monitored for latency and errors.
| Assure user acceptance and usability |  | Ensure the system is understandable and usable by HR stakeholders | User testing with HR staff; feedback loop for improvements.
| Minimize the risks of unforeseen errors |  | Detect and mitigate model failures or anomalies early(< 1% critical error rate) | Input validation; try/except in app; logging of errors.
| Deployment strategy |  | Automate CI/CD, version control, and API integration(CI/CD success rate, Version rollback time, API latency) | Streamlit app; can be containerized for cloud deployment.
Monitoring and Maintenance
| Non-stationary data distribution |  | Data/Concept Drift Metrics (e.g., KS test, PSI, SHAP drift) | Plan for periodic retraining if data drifts.
| Degradation of hardware |  | CPU/GPU usage, Memory, Latency trends | Not a major concern; monitor for slowdowns.
| System updates |  | CI/CD tests, Post-update inference accuracy | Regular code and dependency updates; retrain as needed.
| Monitor |  | Airflow | Manual monitoring; can add logging/dashboard in future.
| Update |  | Update frequency, Model performance before vs. after retrain | Retrain and redeploy model as new data arrives or as performance drops.
Note on C9: Sharat: Define the purpose and the success criteria of the ML application from a business point of view. eg: "sales will increase by 13%".
Note on C10: Sharat: Define the business objective in terms of ML success criteria eg: "accuracy should be greater than 95%"
Note on C11: Sharat: Add an economic success criterion to the project. eg: "cost savings with automated quality check per each product".
Note on C13: Sharat: Proof of concept (PoC): Search for similar applications or similar methods/approaches on a different domain.
Note on C14: Sharat: Identifying Legal issues are essential for any business application. Research all Legal constraints and record them.
Note on C15: Sharat: The requirements include robustness, scalability, explainability and resource demand needed for the development, testing & inference.
Note on C17: Sharat: Modification on the data set should be documented.
Note on C19: Sharat: The data should be described by their statistical properties. Information about format, units, etc., of each feature is required (domain knowledge)
Note on C20: Sharat: The requirements can be the expected feature values (a range for continuous features or a list for discrete features) and the format of the data. Requirements have to be defined carefully to include all possible real world values.
Note on C21: Sharat: The initial data at the start of project and any additional data has to be checked according to the requirements. The best practices to be used for data exploration techniques to investigate the sample distribution have to be recorded.
Note on C24: Sharat: Select a relevant features based on the available data. Features should be analyzed by a domain expert. Feature selection methods can be categorized into three categories: 1) filter methods: selects features from data without considering the model 2) wrapper methods: uses a learning model to evaluate the significance of the features 3) embedded methods: combination of above two methods
Note on C25: Sharat: Discard the samples strictly based on objective quality criteria. Criteria for selecting or not selecting the observations should be clearly documented.
Note on C26: Sharat: Verify for Imbalance in the Data. Trying out different sampling techniques could improve the results. Comparing the results of different sampling techniques’ reduces the risk of introducing bias in the model.
Note on C28: Sharat: Noise/irrelevant features should be filtered to improve the signal-to-noise ratio. Filtered data to be documented and evaluated. Caution: Filter could remove important parts of the data.
Note on C29: Sharat: Missing, NAN and special values could be imputed with a model readable value. To reduce the risk of introducing substitution artifacts, the performance of the model should be compared by trying different imputation techniques.
Note on C31: Sharat: New features could be derived from existing ones based on domain knowledge.
Note on C32: Sharat: Data augmentation is getting more data from existing data.
Note on C34: Sharat: Document the file format in which you have the data needed for training the model. The comma separated values (CSV) format is the most generic standard.
Note on C35: Sharat: Features could be defined on different scales and might lead to strong bias when we have features which are of smaller scale and larger scale, hence normalization is required.
Note on A36: Sharat: The goal of the modeling phase is to craft one or multiple models that meet the objectives and constraints. The choice of modeling techniques depends on the ML and the business objectives, the data and the industry, demography of project etc.
Note on C37: Sharat: Research the publications, patents, internal reports, etc for existing solutions on the business problem that we are working on.
Note on C38: Sharat: Evaluate the models on at least six key parameters
Note on C39: Sharat: Accuracy / performance on unseen data
Note on C40: Sharat: Resiliency to inconsistent inputs and to failures in the execution environment
Note on C41: Sharat: Ability to scale to high data volume in the production system
Note on C42: Sharat: Direct or post-hoc explainability
Note on C43: Sharat: Capacity should suit the data complexity
Note on C44: Sharat: Resource consumption/demand for deployment
Note on C45: Sharat: The model selection depends on the data and has to be tailored to the problem.
Note on C46: Sharat: Adding domain knowledge should always increase the quality of the model. It is best practice to validate the incorporated domain knowledge with respect to a general model.
Note on C47: Sharat: The trained model depends on the learning problem and as such are tightly coupled. The learning problem contains an objective, optimizer, regularization and cross-validation.
Note on C48: Sharat: Labeling data could be very expensive and might limit the available data set size. Perform techniques like unsupervised pre-training and semi-supervised learning to handle unlabeled data.
Note on C49: Sharat: Compression or pruning methods could be used to obtain a more compact model.
Note on C50: Sharat:
Note on C51: Sharat: ML models are difficult to reproduce. To accept the models to generalised conditions reproducibility is a primary characteristic.
Note on C52: Sharat: Reproducing the model from an extensive description or sharing of the used algorithm, data set, hyper-parameters and production environment.
Note on C53: Sharat: Large performance variances indicate the sensitivity of the algorithm and question the robustness of the model.
Note on C54: Sharat: Keeping track of the changed model’s performance and its causes allows model comprehension by addressing which modifications were beneficial and improve the overall model quality.
Note on C56: Sharat: A major risk is that the test set cannot cover all possible inputs due to the large input dimensionality or exceptional cases. It is recommended to separate the teams and the procedures collecting the training and the test data to erase dependencies and avoid methodology dependence.
Note on C57: Sharat: A major risk occurs if ML applications are not robust to noisy or wrong, or even designed adversarial input data. Verification approaches and robustness validation methods using cross-validation techniques on historical data exist.
Note on C58: Sharat: Explainability of a model helps to find errors and allows strategies, e.g. by enriching the data set, to improve the overall performance.
Note on C59: Sharat: Domain and ML experts have to decide if the model can be deployed. The best practice is to document the results of the evaluation phase and compare them to the business and ML success criteria defined.
Note on C61: Sharat: Selecting the right hardware based on the requirements defined in the initial stages or align with an existing hardware. Cloud services offer scalable computation resources, but they have hard constraints.
Note on C62: Sharat: The best practice to evaluate the performance of the model under incrementally increasing production conditions by iteratively running the tasks.
Note on C63: Sharat: The best practice is to build a prototype and run an field test with end users. Examine the acceptance, usage rate and the user experience.
Note on C64: Sharat: Unforeseen errors and outage times could cause system shutdowns and a temporary suspension of services. A fall-back plan, that is activated in case of e.g. erroneous model updates or detected bugs is helpful.
Note on C65: Sharat: Before rolling out a model, it is best practice to setup incremental deployment strategy that includes pipeline for models and data.
Note on C66: Sharat: ML models are used over a long period and have a life cycle which has to be managed. The risk of not maintaining the model is the degradation of the performance over time which leads to false predictions and could cause errors in subsequent systems.
Note on C67: Sharat: A shift in the data distribution of features is possible. This degrades the performance of the model over time.
Note on C68: Sharat: The hardware that the model is deployed on and the sensor hardware will age over time.
Note on C69: Sharat: Updates on the software or hardware of the system can cause a shift in the environment.
Note on C70: Sharat: Monitor all input signals and notify when an update has occurred. The statistics of the incoming data and the predicted labels can be compared to the statistics of the training data. This phase also includes a comparison of the performance with the defined success criteria.
Note on C71: Sharat: Instead of training a completely new model from scratch, it is advised to fine-tune the existing model to new data. The performance of the updated model should be compared against the previous versions and could give insights on the time scale of model degradation. The automation of the update strategy can be boosted up to a continuous training and continuous deployment of the ML application while covering the defined quality assurance methods.